## How to use this
FMEA — Failure Modes and Effects Analysis
This sheet helps you decide what to fix first. You list everything that can go wrong, score each one three ways, and the workbook multiplies those scores into a single risk number so you can rank them.
What to do, in order
1. Open the FMEA tab. Row 1 is a worked example — read it, then overwrite or delete it.
2. In column A, list your process steps. Take them straight from your process map.
3. For each step, write what can go wrong (column B) and what that does to the customer (column C).
4. Score SEVERITY, OCCURRENCE and DETECTION from 1 to 10 using the Scoring guide tab. The cells will refuse anything outside 1–10.
5. RPN calculates itself. Sort by it, highest first.
6. Write actions for the worst ones, then re-score in the New SEV / OCC / DET columns after you have made the change.
Two rules that matter more than the maths
Never ignore a severity of 9 or 10 just because its RPN is low. A rare catastrophe still needs a control.
In support, detection is nearly always 8–10, because most failures are only found when the customer contacts you a second time. Score that honestly and your priorities will change completely.
When you are done
The failure modes with the highest RPN become candidate root causes to test in the Analyze phase, and the controls you design for them belong in your control plan.

## FMEA
FMEA — Failure Modes and Effects Analysis
Find the failure modes that will hurt most, and fix those first. RPN and New RPN calculate themselves.
HOW TO USE THIS SHEET
Yellow cells | You fill these in. Blue text = a number you typed.
Blue cells | Calculated for you. Do not type over these — they contain formulas.
Row 1 example | A realistic worked example, so you can see the expected format. Delete or overwrite it.
SCORE EACH FAILURE MODE 1–10 ON SEVERITY, OCCURRENCE AND DETECTION. THE SCORING GUIDE IS ON THE NEXT SHEET.
Process step | Potential failure mode | Effect on the customer | SEV | Potential cause | OCC | Prevention control | Detection control | DET | RPN | Recommended action | Owner | Due | Action taken | New SEV | New OCC | New DET | New RPN | rank | # | Failure mode | RPN now | RPN after | Act above
Agent closes a billing ticket | Adjustment has not posted yet | Customer discovers it themselves and contacts us again | 7 | System closes the ticket before the posting webhook confirms | 8 | None | Only detected if the customer complains again | 9 |  | Block Resolved status until the posting webhook confirms | Billing Ops | 2026-09-30 | Deferred-close rule shipped | 7 | 2 | 3 |  |  | 1
Tier 1 tags the contact reason | Wrong reason selected | Routing sends it to the wrong queue; customer repeats themselves | 6 | 40 codes in a flat list, no search | 9 | Annual training | QA audit catches it weeks later on 2% of contacts | 8 |  | Cut the list to 12 codes and predict from the first message | Support Ops | 2026-10-15 | Code list redesigned, pending release | 6 | 3 | 4 |  |  | 2
Billing Ops verifies evidence | Evidence missing, ticket bounced back | Adds a full day to the resolution | 5 | Tier 1 has no checklist for what Billing needs | 7 | Wiki page nobody opens | Detected immediately on bounce-back | 3 |  | Required-fields form before hand-off | Support Ops | 2026-09-15 | Form live since August | 5 | 2 | 3 |  |  | 3
Nightly adjustment batch runs | Batch fails silently | Every adjustment that day is late; nobody knows until customers call | 8 | No alerting on batch exit code | 4 | None | Discovered next morning by chance | 9 |  | Alert on non-zero exit to the on-call channel | Platform Eng | 2026-09-01 | Alerting deployed | 8 | 2 | 2 |  |  | 4
Agent applies a goodwill credit | Credit exceeds the agent's authority | Margin leakage; caught in month-end reconciliation | 4 | Limit is documented but not enforced in the tool | 6 | SOP states the limit | Month-end reconciliation, up to 30 days later | 7 |  | Enforce the limit in the credit form | Billing Ops | 2026-11-30 | In backlog | 4 | 6 | 7 |  |  | 5
Customer confirms resolution | No confirmation ever arrives | Ticket auto-closes while the customer still has the problem | 6 | Auto-close at 96 hours with no reminder | 7 | None | Only visible as a reopen days later | 8 |  | Send a reminder at 48 hours before auto-close | Support Ops | 2026-10-01 | Reminder shipped | 6 | 3 | 4 |  |  | 6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
SUMMARY
Failure modes logged
Highest RPN
Above 200 (act now)
Severity 9 or 10 (act regardless of RPN)
Average RPN before
Average RPN after
Risk reduction (on remediated rows)
KEY INSIGHT FOR SUPPORT: detection is usually terrible (8–10). Most support failures are only detected if the customer complains a second time. Score every step whose only detection mechanism is "the customer contacts us again" as 9 or 10 — that scoring alone reprioritises most support FMEAs.

## Scoring guide
How to score severity, occurrence and detection
Use these anchors so two people scoring the same failure mode land in the same place.
SEVERITY — how badly does this hurt the customer?
Score | What it means
1–2 | The customer does not notice.
3–4 | Minor annoyance. No extra effort for the customer.
5–6 | The customer has to follow up, or wait noticeably longer.
7–8 | The customer escalates, complains, or becomes a churn risk.
9–10 | Regulatory breach, safety issue, data exposure, or mass impact.
OCCURRENCE — how often does it happen?
Score | What it means
1–2 | Once a year or less.
3–4 | About monthly.
5–6 | About weekly.
7–8 | Daily.
9–10 | On most contacts of this type.
DETECTION — would we catch it before the customer does? (10 = we would not)
Score | What it means
1–2 | An automated control blocks it from happening at all.
3–4 | The system flags it the moment it occurs.
5–6 | QA sampling would catch it eventually.
7–8 | A supervisor might spot it.
9–10 | Only detected if the customer contacts us again. ← most support failures live here.