## How to use this
Yellow cells
You fill these in.
Blue cells
Calculated for you. Do not type over them — they contain formulas.
Green row
A worked example so you can see the expected format. Delete it when you start.
What this is for
Finding the person who can stop your project before they do, and settling who owns what while it is cheap.
Stakeholders tab
Score influence 1-5 and support -2 to +2 honestly. The Action column works out who to deal with first: high influence and opposed is where projects die.
RACI tab
The count column flags any row that does not have exactly one Accountable. Fix every flag before you leave the tollgate — 'we are both accountable' means nobody is.

## Stakeholders
Stakeholder analysis — who can stop this, and who will
Projects rarely fail on the statistics. They fail because someone with influence was never asked.
Name | Role | Influence 1-5 | Support -2..+2 | Action needed | What they need from you | Owner
A. Okafor | Billing Ops Manager | 5 | -1 |  | Proof this will not add work to her team | Black Belt
SUMMARY
Stakeholders mapped
High influence and opposed — deal with these first
High influence and supportive — your sponsors

## RACI
RACI — exactly one Accountable per row
Two names in the Accountable column is the most common reason a control plan quietly stops being executed.
Activity / decision | Black Belt | Champion | Process owner | WFM | Finance | Accountable count
Sign the benefit and harvest mechanism | C | A | C | C | R
R = does the work · A = owns the outcome (exactly one) · C = asked before the decision · I = told after it.